# Blockchain-Based Identity and Provenance for Distributed Energy Assets

Immutable Identity, Lifecycle Traceability, and Integrity Verification for Solar and Renewable Infrastructure

[AUTHOR NAME — TO BE SUPPLIED]

Table of Contents

# Part IV — Application and Deployment

# Case Study — Solar Asset Identity Pilot Architecture

## What This Chapter Covers

Everything so far has been architecture in the abstract. This chapter assembles it into one concrete system: a composite design walkthrough of a 50 MW single-axis-tracking plant, synthesized from the research program in which the defect-mapping work of Chapter 6 was developed and from published industry practice on comparable deployments. It is not a field report of one named commercial project. Metrics labeled illustrative are engineering estimates calibrated to the architecture’s models (Chapters 6–7, 13); metrics labeled archetype actual are drawn from anonymized program records the author has permission to cite once publication clearances are complete (see this chapter’s references). The presentation is at the level an implementing engineer needs — build phases and their true proportions, system diagram, participant layout, data flows for five representative scenarios, smart-contract logic in walkthrough form (full listings in Appendix A), results with caveats attached, and what an honest case study should preserve: what went wrong, what was redesigned, which problems remain open, and what a successor program would do differently. Where a parameter is site- or program-specific I say so; the intent is that the chapter functions as a replicable design template, not a sales exhibit.

## 11.1 Pilot Scope and Ground Rules

The plant. 50 MW(DC) single-axis tracking; ~126,000 bifacial modules of a single OEM across two production lines; 340 string inverters; 1,260 tracker rows. Chosen deliberately mid-scale: large enough that per-unit manual process fails visibly, small enough that one EPC and one O&M contractor cover the field side. The single-OEM simplification is acknowledged as the design’s largest departure from market reality — multi-vendor plants are the norm, and they would have forced the cross-vendor template problem (Section 11.7, problem 2) into the critical path rather than the research agenda. The program chose to prove the vertical slice first and carry the horizontal question forward; a successor program should invert that choice.

The participants and their nodes. Eight consortium members at pilot stage — module OEM, inverter OEM, EPC, owner (an infrastructure fund), O&M contractor, insurer, an independent engineering/certification firm, and a university lab operating the Tier-3 reference instruments (Section 6.7). Eight validators is below Section 7.5’s target range; the consortium agreement (Section 11.6) provides for expansion to 12–16 with the second plant, and the pilot accepts the weaker (f = 2) fault bound as a documented, temporary risk.

The role assignments follow Part II’s logic deliberately: both OEMs hold registrar accreditations for their own products; the certifier and university carry the accreditation-committee load precisely because they sell nothing into the plant; and the O&M contractor — the party lesson 3 will feature — was given a technical-committee seat at the owner’s insistence, over objections the S2 episode retroactively settled in the owner’s favor. Recruitment order mattered and is reported for successors. The insurer signed first — Chapter 13’s incidence analysis predicts exactly this, and its early commitment converted two hesitant parties (the owner, whose fund wanted the diligence-cost story validated by the party who would pay it, and the OEM, for whom the insurer’s participation reframed enrollment from compliance cost to product feature). The EPC signed last and under commercial persuasion (a preferred-bidder consideration on the owner’s next project), which foreshadowed the S2 friction: the party with the least to gain from evidence is the party whose workflows generate the most of it, and successors should price that asymmetry into their recruitment rather than discovering it in week three of commissioning. Each member’s motivations were documented in the program charter — a practice recommended without reservation, since half of governance is remembering why everyone came.

Tiering decisions. Tier 0 enrollment (factory EL + flash VC) for all 126,000 modules; magnetometric (Tier 2) enrollment for a 5% stratified sample (6,300 modules) plus both production lines’ first-article sets — sized to give population-level statistics for the R2 stability study (Section 6.8) while bounding instrument time on a production-paced line; active binding (secure elements) in all 340 inverters, whose vendor shipped ML-DSA-capable elements — the hybrid-signing regime of Section 9.3 applied from day one. The 5% figure was the resolution of a genuine argument: the research side wanted 20% for statistical power, the factory wanted 1% for line impact, and the compromise was set by the defect-map station’s throughput (one unit per four minutes against a 25-second takt) — an instance of Section 6.2’s maturity honesty pricing itself into a real program, and a number that successors with faster instruments should revisit upward.

Ground rules for the account. Four disciplines govern how the walkthrough is reported here. (1) Evidentiary class: every number is tagged illustrative (engineering estimate from the architecture’s models), archetype actual (anonymized program datum, pending formal citation), or sector baseline (published industry or insurer practice). (2) Composite narrative: scenarios S1–S5 are representative of events observed across research and industry programs; they are not presented as a single chronological audit log unless explicitly labeled. (3) Failures are reported with their costs, because a case study’s negative results are its most transferable content. (4) Generalization limits — one OEM, one climate, one regulatory context — are flagged wherever they bind, with Chapter 12 carrying the generalization burden this walkthrough cannot. Program identities are withheld pending sponsors’ publication clearances; formal technical-report citations appear in this chapter’s references as [PROGRAM TECHNICAL REPORTS — TO BE SUPPLIED AT PRESS TIME].

### 11.1.1 The Build, Phase by Phase

The program ran in five overlapping phases, and the calendar is itself a finding — where the time actually went contradicts where the industry assumes it goes.

Phase 0 — Constitution (four months). The consortium agreement (the Section 10.5 checklist, negotiated to signature), accreditation criteria, custody contracts, and fee schedule. Longest-feeling phase, entirely lawyers and committees, and in retrospect under-resourced: two governance questions deferred here (the co-signing window, the sub-tier work-order integration) returned as the year’s two operational incidents. The phase’s one unqualified success was sequencing the agreement before any technology procurement — every vendor conversation thereafter happened against decided requirements rather than shaping them, an ordering the first-wave consortium histories of Section 1.5 recommend by counterexample.

Phase 1 — Factory integration (three months, overlapping). Registrar agent development against the OEM’s manufacturing-execution system, secure-element retrofit boards for the existing EL and flash stations, HSM ceremonies, and the enrollment exception paths of Section 4.3.1. The integration consumed roughly four times the effort of the ledger deployment itself — the ratio Section 7.6’s cost model warns about, here measured — and its critical-path item was neither software nor silicon but the factory’s own change-control process, which treats any modification to a qualified production line with a conservatism the program learned to schedule around rather than argue with.

Phase 2 — Ledger and custody (six weeks). Validator deployment across the eight members, contract suite audit and deployment, anchoring agents against two public chains, custody stores with retrievability challenges. The shortest phase, as Chapter 7 predicted: consensus infrastructure at these loads is genuinely small, and the phase’s only schedule event was an HSM shipment stuck in customs — a sentence the program’s blockchain skeptics have enjoyed ever since.

Phase 3 — Field tooling (four months, overlapping construction). Handheld verification kits, work-order system integration for the O&M prime, inverter commissioning self-attestation firmware, and drone campaign tooling. The phase that generated the most schedule risk, because it coupled to the EPC’s construction calendar, which no software plan controls — the inverter firmware in particular shipped in the last week it usefully could have, after a certification-lab queue the program had not budgeted, and successors should book that lab slot at kickoff.

Phase 4 — Operations and exercises (ongoing). Commissioning at construction pace, the verification and adjudication scenarios of Section 11.3, the first governance year of Section 11.6, and the disaster-recovery exercise of Section 7.7. Go-live was not an event but a gradient: the first anchored registration preceded the last governance signature by a month, which the program tolerated and a purist would not have.

The budget’s shape, in ratios rather than figures the program cannot publish: integration engineering (Phases 1 and 3) took roughly half the total; constitution, legal, and governance a fifth; instruments and retrofit hardware a fifth; and the ledger, custody, and anchoring infrastructure — the part the word “blockchain” evokes — under a tenth. The ratios are the chapter’s most quotable finding for anyone budgeting a successor, and they echo Section 7.6.1’s cost-model omissions almost exactly: the architecture’s expensive parts are its edges, where it touches factories, crews, and lawyers, not its center.

Security practice ran alongside from Phase 2: the contract audits noted above, a tabletop governance-capture exercise in the first quarter of operations (Section 8.7’s cheap annual rehearsal — three findings, all procedural), and a scoped physical red-team in month nine whose ringer attempt against a mock verification produced the position-photograph procedure now standard in Section 8.3. The program’s security spend followed Chapter 8’s budget-allocation memo — heaviest at enrollment and accreditation, lightest at consensus — and the year’s incident record (zero ledger-layer events, every incident procedural) is consistent with the allocation having been right.

## 11.2 System Architecture

Figure 11.1 Pilot system diagram. Shaded components are the three zones of Figure 10.1; arrows show the dominant data flows, quantified in Section 11.2.1. Every organization hosts its own boxes on its own infrastructure — the validator set spans four hosting arrangements and three jurisdictions, per Section 4.7’s anti-correlation rule.

flowchart TB
    subgraph FACTORY [Factory - module OEM]
        ELI[In-line EL + flash<br>instrument DIDs] --> RA[Registrar agent:<br>batching, Merkle roots]
        QDM[Tier-2 defect-map<br>station, sampled] --> RA
    end
    subgraph FIELD [Site - EPC then O&M]
        HH[Handheld verify kit:<br>EL spot + challenge app]
        INV[340 inverters:<br>secure-element DIDs,<br>self-attesting commissioning]
        DRONE[Drone IR / EL<br>campaign rigs]
    end
    subgraph CONS [Consortium zone - 8 validators]
        LED[(BFT ledger:<br>registry + lifecycle<br>contracts)]
        MON[Cohort monitor:<br>read-side analytics]
    end
    subgraph CTRL [Controlled zone]
        PAY[(Payload custody ×3:<br>owner, OEM, archival)]
        PREG[(Party registry:<br>role DIDs)]
    end
    subgraph PUBZ [Public zone]
        ANC1[Anchor chain A]
        ANC2[Anchor chain B]
    end
    RA --> LED
    RA --> PAY
    HH --> LED
    INV --> LED
    DRONE --> PAY
    DRONE --> LED
    LED --> ANC1
    LED --> ANC2
    MON --> LED
    PREG -.-> LED
    INS[Insurer / buyer<br>verification clients] --> LED
    INS --> ANC1
    INS -.authorized.-> PAY

### 11.2.1 The Data Flows in Numbers

Figure 11.1’s arrows, quantified over the pilot year, because a diagram with magnitudes is an architecture and without them a poster. Factory to ledger: ~1,150 batch transactions committing 126,000 registrations and their shipping events — kilobytes per shift, exactly as Chapter 7 modeled. Factory to custody: 9.4 TB of enrollment payloads (EL images dominating; the 6,300 Tier-2 defect maps contributing 2.1 TB), written three ways. Field to ledger: ~410,000 events across commissioning, custody, maintenance, and inspection — the plant’s entire evidential year fitting in under half a gigabyte of envelopes. Site to custody: 3.8 TB of commissioning and campaign imagery. Anchor agents to public chains: 2,920 anchor transactions (four daily, two chains), total fees under USD 900 at observed rates — the year’s cheapest line item, per lesson 4 its highest- credibility one. Read side: the insurer’s client verified ~2.3 M envelope-proof pairs (continuous Step-1 over its book); the mock-buyer exercise added ~40,000; replica queries otherwise stayed in the low millions, served from two read replicas whose combined load never exceeded what one laptop could serve. Every number lands within the Chapter 7 model’s error bars, which is the sentence this subsection exists to earn.

Platform notes, kept to one paragraph because Section 2.6 promised platform neutrality: the pilot runs a permissioned BFT ledger (a Fabric-family stack was selected for its mature channel and endorsement tooling; the schema and contracts are written against the Chapter 5 envelope so that the platform is replaceable), anchored four times daily to two unrelated public PoS chains. Payload custody is object storage at three organizations under the proof-of-retrievability regime of Section 4.2, challenged weekly. The cohort monitor is an ordinary analytics service with no write authority — Section 5.5’s constitution-not-police principle made operational.

Three architecture decisions that Figure 11.1 renders as boxes deserve their reasons as prose. The handheld kits are deliberately dual-mode: online against read replicas when coverage allows, and offline against cached header checkpoints and pre-loaded record bundles when it does not — because the site’s cellular coverage map was, characteristically, worst exactly where the racking was densest, and a verification tool that needs bars is a tool crews abandon. The insurer’s clients run entirely outside the consortium (Section 2.4’s read-permission design): the insurer chose, deliberately and instructively, to consume public headers plus authorized disclosures rather than take a validator seat in year one — its stated reason being that reliance would be more persuasive to its own auditors if it demonstrably required no operational entanglement. And the university lab holds the Tier-3 reference role with its instruments and its independence — the metrological anchor of Section 6.7’s recursion — plus, in practice, the informal role every deployment should staff: the party whose only stake is that the measurements be right, and whose presence in committee reliably lowered the temperature of commercial arguments.

## 11.3 Four Scenarios, Walked End to End

The four scenarios were chosen at program design as the value-bearing paths the pilot existed to prove — one per stakeholder whose adoption Chapter 13 identifies as decisive (factory, project delivery, insurance, adjudication) — and instrumented from day one, which is why this section can report numbers rather than impressions.

S1 — Production day. The scenario that had to be boring for the program to survive, and was. Each line emits ~1,400 modules/shift. Per module: EL capture and flash test in the existing QA cell (cycle cost of enrollment: the template extraction, ~2 s of compute, zero added handling — the Section 4.3 economics realized); registrar agent accumulates envelopes, builds a 2,048-leaf Merkle batch, writes the manifest to all three custody stores, then submits the root (Section 7.2 verbatim). Tier-2 sampled units detour ~4 min to the defect-map station — the one process change the factory noticed, absorbed by sampling rate. Measured pilot figures: 3–4 batch transactions per shift per line; registration lag (lamination to anchored DID) median 6.2 h, dominated by anchor cadence, which is fine — nothing downstream consumes a DID faster than shipping does.

The exception statistics tell the operational story the happy path hides. Across the production campaign: 0.8% of units entered the rework loop and were correctly re-enrolled under superseding events (Section 4.3.1’s re-test path, exercised ~1,000 times without incident); 0.02% hit label–structure mismatches at the station’s final check — all mis-fed label stock, all quarantined automatically, none escaping; and one instrument fault (a flash tester’s signing board failing mid-shift) triggered the deferred-enrollment path for 212 units, which flowed to the backup station within the shift. Two findings from the statistics themselves: the rework-loop enrollment history turned out to be wanted by the OEM’s quality team as process telemetry they had never had per-unit before (an unplanned benefit that eased the factory’s tolerance of the whole program), and the exception rates stabilized within three weeks — the workforce learning curve was short because, per the design intent, almost nothing about the work changed.

The logistics leg between S1 and S2 ran the dual-signed custody protocol at container scale: 152 consignments, each a EVT_SHIP plus custody transfers at consolidation, port, and site laydown, with receiving inspections sampling V1 checks per Section 3.6’s ladder. Yield: three exception-noted receipts (two crushed pallet corners, one count discrepancy resolved as a manifest error), each dual-attested at the dock in the manner Section 5.3 designed — and, months later, the transport insurer’s renewal quote for the owner’s next project cited the consignment record quality explicitly, the first commercial pricing signal the program observed in the wild.

S2 — Commissioning. The event that starts 126,000 warranty clocks. String-by- string: EPC runs IV/insulation tests with instrument-DID’d testers; inverters self-attest their commissioning readings under their secure-element identities (active binding earning its keep — no transcription step); owner’s engineer co-signs per Class C; EVT_COMMISSION batches land per Figure 5.2’s enforcement. The pilot’s first governance fight happened here and is reported honestly in Section 11.5: the EPC’s schedule pressure collided with the corroboration requirement, and the resolution — a 72-hour co-signing window with events valid from claimed-time — is now the schema’s recommended default.

The commissioning payload’s contents, since successors will copy them: per string, the IV curve and insulation-resistance test payloads (instrument-signed, grade I-A), torque-check confirmations (grade I-C, operator-attested — the honest label for a wrench), the string’s position map delta against the installation record, and the inverter’s self-attested commissioning readings; per block, the grid-connection references and protection-settings attestations the DSO interface of Section 10.4 consumes. The whole payload set maps onto IEC 62446-1’s documentation checklist per Table 5.5 — the commissioning engineer recognized every artifact, which was the design’s intent and the reason adoption survived the schedule fight.

The fight deserves its blow-by-blow because every deployment will have it. Week three of commissioning, the owner’s engineer — one person, covering two other projects — fell four days behind the EPC’s string-completion rate; the contract’s write-time Class C check rejected the EPC’s submissions; the EPC, facing liquidated-damages exposure on the interconnection milestone, demanded the corroboration requirement be waived; the owner, correctly, refused to gut the warranty evidence its fund’s investment committee had been sold on. The technical committee’s resolution took nine days and one amendment: events accepted with the engineer’s co-signature arriving up to 72 hours after the EPC’s submission, valid from claimed time, with the gap itself recorded — so schedule reality was accommodated, the corroboration survived, and a co-signing lag statistic now exists that the monitor watches (a lag trending toward its window is an early warning of exactly the resourcing failure that caused the episode). The transferable lesson is not the 72-hour number but the method: when schedule and evidence collide, the answer is asynchrony with the gap recorded, never waiver with the gap hidden.

S3 — The insurer’s annual verification. The Chapter 6 workflow as a subscription — and the scenario the insurer’s own board had made a condition of its program participation, which concentrated minds: Step 1–2 (record authenticity + evidence-graph policy) run continuously by the insurer’s client against headers and anchors; Step 3 annually — sampling design (n = 380, stratified by production week and string position, 95/5 confidence on the fleet fraction outside degradation envelope) committed to the ledger before the site visit; handheld EL challenge-verification of the sample against enrolled templates, with 12 units escalated to portable magnetometry. Year-one outcome: 378/380 template matches; 2 mismatches traced to a documented pallet-drop replacement never event-logged — an honest completeness failure (Section 5.7) that cost the O&M contractor a finding and produced the pilot’s procedural fix: removal/replacement events are now blocking steps in the work-order system, not after-action paperwork.

The sampling design itself, committed as evt:s3-2027-design before the visit: stratification by production week (14 strata) crossed with string position class (edge/interior, a PID-risk proxy), allocation proportional to stratum size with a floor of eight units per stratum, selection by a published seeded generator over the frozen as-installed register, and the escalation rule (any mismatch inflates its stratum’s sample threefold) pre-declared. None of this is statistically exotic — it is Cochran’s textbook with a ledger commitment — and that ordinariness is the point: the adversarial soundness comes from the pre-commitment, not from novel mathematics, per Section 6.6.1.

The campaign’s operational texture, for the practitioner who will run one: two technicians, nine field days (Section 11.7’s ergonomics problem is why it was not six), night work for the EL rig on 340 of the sampled units and daylight contact measurement for the rest; unit selection executed at the racking per the anti-ringer procedure of Section 8.3, with the position photographs adding perhaps ninety seconds per unit and one flagged discrepancy (a transposed row label from construction, corrected as a finding rather than a fraud). The twelve magnetometric escalations were chosen where EL matches were positive but marginal — all twelve confirmed identity and quantified condition deltas that EL alone had bounded loosely, which is the escalation tier doing precisely its Section 6.7 job. The insurer’s diligence cost, all-in against its prior-year conventional baseline for a comparable plant: 40% — with the pre-committed sampling design surviving its first hostile review when the owner’s fund auditors, initially skeptical that 380 units could speak for 126,000, were walked through the acceptance-sampling arithmetic their own procurement standards already used.

The insurer’s continuous Step-1/2 subscription deserves its own line in the record: across the year it processed every new event on the covered fleet within minutes of anchoring, raised four policy flags (two instrument-grade downgrades, one cadence anomaly that proved to be a paused cleaning contract, and the S3 finding’s precursor), and cost the insurer, by its own account, one analyst-day a month to operate — the “verification as subscription” economics that Chapter 13 builds on.

The two mismatches deserve their epilogue because they exercised the whole escalation machine: re-measurement excluded instrument error; template comparison against the corpus (the F4 resurrection check) identified both units as enrolled modules from the same production batch — physically genuine, correctly enrolled, but sitting at positions whose records said other modules sat there. The work-order archaeology took an afternoon: a pallet dropped during construction, two damaged modules swapped for spares by a subcontractor crew, no event filed. Honest units, dishonest- looking records, a procedural fix — and a demonstration to every party watching that the system distinguishes fraud from sloppiness by evidence rather than by accusation, which did more for the O&M relationship than the finding cost it.

S4 — Warranty adjudication rehearsal. A staged dispute (real modules, agreed fiction, both parties’ real counsel and a real arbitrator engaged under the program’s budget): owner claims accelerated degradation on 210 modules of one production week. The evidence DAG did what Chapter 5 designed it to do: claim event references commissioning + three condition records; OEM’s response references the same records plus factory Tier-2 first-article maps; the adjudicating engineer re-executed the provenance chains (Section 4.5’s determinism paying off — two processing-version pins had to be honored, exactly as Section 4.2 predicted) and resolved in 11 days against a sector norm of months. The rehearsal’s real product was the finding that both parties’ counsel accepted anchored ledger extracts without contesting authenticity — the first indication that Step-1 verification has the evidentiary standing the whole design wagers on.

The rehearsal’s all-in cost — adjudicator fees, counsel time on both sides, the sampling campaign, and program staff — came to roughly a tenth of the OEM’s reported average for comparable live disputes, with the usual caveat that a rehearsal lacks a real dispute’s motivated obstruction. The eleven days decompose instructively: two for pleadings against the stipulated-evidence clause (Section 10.3’s arbitration design, exercised); five for the adjudicator’s independent re-execution of the evidence graph — including the deliberately planted complication, a condition record whose processing pipeline version had been superseded mid-pilot (lesson 6 below), which the versioned re-execution machinery resolved in an afternoon that would otherwise have been an expert-witness week; three for the physical sampling of contested units under the challenge protocol; one for the award. The staged fiction was calibrated from real disputes in the OEM’s claims history, and the participating counsel’s debrief produced the quote the program’s steering committee circulated most: the dispute was “argued about causation from day one, because there was nothing else left to argue about” — which is, compressed to a sentence, the entire value proposition of Part II.

S5 — The unplanned scenario: a secondary-market rehearsal. Late in the year, the owner’s fund asked the program to mock a partial divestment — 5,000 modules from an early production week, packaged for a hypothetical buyer’s diligence — because its investment committee wanted to see the resale story with its own eyes. The exercise assembled the disclosure bundle of Section 10.2.2 (registrations, commissioning, condition chains, climate-zone class, verifier attestations) in two days of analyst time, most of it spent deciding what not to disclose — the first live exercise of the selective-disclosure policy, which held. A diligence firm engaged as the mock buyer ran Steps 1–2 in an afternoon, requested V2 sampling of 40 units (executed within the week during a scheduled O&M campaign), and returned a diligence memo whose residual-risk section quoted Table 8.3’s categories nearly verbatim — evidence that the residual-register discipline travels to third parties unprompted. No price was set (the divestment was fictional), so the exercise produced no premium datum for Section 11.7’s problem 5 — but the fund’s committee saw a five-day diligence cycle on an asset class whose norm is six weeks, and the program counts their subsequent enthusiasm as its most consequential unmeasured result. The scenario’s other yield was procedural: the disclosure-policy decisions made under a fictional deadline are now the template the real transaction will start from, which is what rehearsals are for.

## 11.4 The Contract Suite in Walkthrough

Four contracts, deliberately small (Section 8.5, F8); full annotated listings are Appendix A.

Table 11.1 Pilot contract suite. Line counts are the deployed implementations’ logic lines, cited to make the smallness-by-design audible: the whole consensus-critical codebase is under 1,700 lines, reviewable in a day by anyone this book has equipped.

| Contract | State held | Enforces | Size (pilot impl.) |
| --- | --- | --- | --- |
| AssetRegistry | DID → registration record, batch roots | Uniqueness; registrar accreditation; registration class labeling | ~400 lines |
| LifecycleSM | DID → state, custody/ownership registers | Figure 5.1 transitions; Table 5.1 corroboration classes; submission windows | ~700 lines |
| RoleAccred | Role DID → accreditation, algorithm policy, validity intervals | §8.5 succession; §9.4 P2 time-contextual verification | ~300 lines |
| AnchorAudit | Anchor log, custody-challenge log | §4.4 cadence; §4.2 retrievability challenge outcomes | ~250 lines |

The walkthrough example the appendix develops line by line is the LifecycleSM path for EVT_COMMISSION (Figure 5.2’s sequence as code), chosen because it exercises every enforcement class: state check, role check via RoleAccred, corroboration counting, window arithmetic, and the emission of the derived warranty-clock event that the insurer’s client subscribes to.

The reason-code taxonomy deserves its operational note: 71 codes at go-live, organized by the four enforcement classes of Section 5.5, each carrying a documentation link and a suggested remediation. Field telemetry on rejections became an accidental quality instrument — the distribution of reason codes by submitter identified integration bugs (one code spiking from one party is a software defect; the same code spread evenly is a schema usability problem), and two payload-schema clarifications in the year’s amendments originated as reason-code statistics rather than as anyone’s complaint. A rejection, properly coded, is the system teaching its users; uncoded, it is the system training them to route around it.

The suite’s engineering history in three sentences, because contract processes are argued about more than they are documented. Both implementations (the software-diversity rule of Section 7.5 applied from day one, at the cost of roughly 1.6× the single-implementation effort) were developed against the schema’s conformance suite — 412 cases at go-live, grown to over 600 by year-end as every governance amendment and every incident added its regression — and audited independently, with the audit finding two genuine defects: a submission-window boundary condition (off-by-one at exactly the window’s edge, the classic) and a corroboration-counting path that accepted two attestations from instruments sharing a controller, violating Section 4.5’s independence requirement — the precise F8-enables-F5 coupling Chapter 8 predicted, and an audit finding that paid for the audit. Post-go-live change traffic was modest and entirely parameter-level: the S2 window amendment and two payload-schema version registrations, zero logic deployments — the small-contract discipline holding in practice as designed.

## 11.5 Lessons Learned

Reported as they were logged, because sanitized lessons teach nothing.

- The schema survived contact; the procedures did not. No envelope or state-machine change was needed through commissioning. Every early failure was procedural: unlogged replacements (S3), co-signing bottlenecks (S2), a custody store that silently failed retrievability challenges for nine days before its operator noticed the alerts. Systems of this kind fail at the human seams first — design the escalations, not just the cryptography. The corollary the program drew: procedural failure modes deserve the same pre-mortem treatment Chapter 8 gives attacks — enumerate the seams (handoffs, co-signatures, alert routing), assign each a detection and an owner, and rehearse the escalations before the incident chooses its own.

- Enrollment economics behaved as predicted; verification economics beat prediction. Tier-0 enrollment marginal cost was effectively invisible in line takt; the insurer’s Step-3 campaign cost ~40% of its conventional due-diligence baseline because sampling design replaced blanket re-testing. The asymmetry has a lesson inside it: the modeled savings came from the ledger, but the realized savings came from statistics the ledger made defensible — pre-committed sampling was always cheaper than blanket testing, and what the architecture actually sold the insurer’s auditors was the inability of anyone to have gamed the sample.

- The completeness problem is cultural before it is technical. Field crews log what the work-order system forces them to log. The fix that worked was embedding event emission in the tools crews already use — not training, not policy memos. The program’s failed first attempt deserves equal billing: a two-hour training module and a laminated procedure card, which produced two weeks of conscientious logging followed by regression to exactly the prior baseline — a result any behavioral scientist would have predicted and the budget’s training line item did not.

- Anchoring bought unplanned credibility. The S4 finding: external counsel treated public-chain anchors as the decisive authenticity argument, ahead of the consortium’s own signatures. Budget anchoring generously; it is the cheapest trust in the system. The mechanism, per the counsel debrief, is worth recording: the anchors required no explanation of consortium governance, no trust in any party to the dispute, and no expert witness — “the newspaper argument,” one lawyer called it, independently reinventing Section 2.1.2’s framing, and lawyers argue comfortably from precedents they can see.

- Underestimated: instrument identity operations. Calibration-lifecycle events for ~60 instruments (testers, cameras, handhelds, drones) generated more governance traffic than all 126,000 modules — accreditation renewals, firmware attestations, one revoked handheld. Section 4.5’s Rule 3 is right and is also real work; staff it. The revoked handheld is its own paragraph of instruction: a unit whose firmware attestation began failing after a field repair by an unauthorized service shop — no malice found, but the attestation chain was broken and the revocation-and-re-provisioning machinery ran exactly as designed, retiring 3 weeks of that unit’s measurements to grade I-C (operator-attested) status. The measurements survived, downgraded honestly; the procedure held; and the O&M contractor now reads repair terms in its instrument purchase orders.

- The two-layer decomposition needs versioned discipline. Mid-pilot improvement of the stable/condition separation model (Section 6.3) forced the first live exercise of payload versioning and P1-style re-commitment for 6,300 Tier-2 templates. It worked, and it was the strongest validation of Chapter 9’s machinery the pilot produced — migration exercised as routine, not emergency.

- Measure the humans, kindly. The program’s most predictive operational metrics were human-process statistics nobody originally planned to collect: co-signing lag (the S2 early warning), exception- path rates by station and shift (which located a training gap two weeks before it would have become a data-quality incident), and work-order-to- event latency by crew. The kindness matters as much as the measurement: the metrics were reviewed as process health, never as individual performance — the moment field crews suspect the evidence layer is a surveillance layer, Section 5.7’s completeness problem stops being incentive-shaped and becomes adversarial, and no schema survives its own users’ hostility.

- The pilot’s size was nearly too small — and nearly too large. Too small: eight validators left (f = 2), one insolvency away from discomfort, and several governance mechanisms (adverse-interest quorums especially) only barely had the membership to constitute themselves. Too large: 126,000 units meant that every schema mistake had six-figure blast radii, which made the committee conservative in ways a 5 MW sandbox would not have suffered. Programs following this one should consider the two-stage shape the pilot backed into by luck — constitute governance and schema against a small early tranche, then scale the fleet once the amendment traffic settles.

## 11.6 Governance as Deployed

One seat deserves mention for being empty: the program invited the state energy regulator to observe (Section 10.3’s observers-before-members principle), and the invitation was declined for capacity reasons — with a request for the transparency reports instead, which the regulator’s staff have since cited twice in DER data-standards consultations. The half-engagement is reported as encouragement calibrated to reality: regulatory familiarity compounds slowly, starts with documents rather than seats, and begins whenever someone sends the first report.

The Table 10.2 allocations, instantiated: accreditation committee of three (certifier, insurer, university — no party in the module supply chain); technical committee chaired by the owner; contract upgrades by 6-of-8 with a 14-day timelock; migration authority pre-delegated to the technical committee acting with the university lab; party-registry disclosure triggers enumerated (dispute event, regulatory demand, insurance claim above a threshold) with the certifier as contested-case adjudicator; arbitration under the ICC rules seated per the consortium agreement. Two governance events fired in year one — the S2 window amendment (schema policy change, 8-of-8) and one custody-SLA breach finding. Neither reached arbitration. The agreement’s most-used clause, unexpectedly, was the instrument accreditation schedule (lesson 5).

The custody-SLA episode completes the governance record because it exercised the sanctions ladder end to end. The OEM-side custody store failed retrievability challenges for nine consecutive days (lesson 1’s sleeping-alert incident); the audit contract’s third consecutive failure had already triggered automatic re-replication to the archival custodian, so no payload was ever at risk — but the SLA breach stood. The operations committee’s finding imposed the ladder’s second rung (a remediation plan with verification, plus the challenge sampling rate doubled for that store for two quarters) rather than the financial penalty the agreement permitted, reasoning recorded in the finding: first breach, no data exposure, root cause procedural. The store’s operator fixed the alert routing, passed the enhanced regime clean, and the episode now serves as the consortium’s worked example that the ladder’s lower rungs are real — which, per Section 4.3.2’s argument, is what makes the upper rungs credible.

Expansion status at time of writing: the second plant (a different owner, a different module OEM — forcing problem 2 of Section 11.7 onto the roadmap where it belongs) has signed the accession instrument the agreement’s membership clauses anticipated, bringing the validator set to eleven with three further candidates in diligence; the schema required no changes for the new OEM’s enrollment integration, which is the extensibility principle earning its second data point. The federation question — whether growth continues within one consortium or splits along the jurisdictional lines Chapter 7 and 10 recommend — is scheduled for the membership’s second annual meeting, and this book’s advice is on the record.

Governance load, quantified for planners: across year one, the committees consumed roughly 340 person-hours across the eight members — front-loaded into the amendment and accreditation traffic of the first two quarters, decaying toward a steady state near 20 hours a month consortium-wide. Small numbers, deliberately reported: the sector’s consortium-phobia is calibrated on standards-war experiences, and the observed load of governing a running system with decided questions is an order of magnitude below the load of deciding the questions — one more argument for Phase 0 patience.

## 11.7 Open Engineering Problems, From the Field

Continuing Section 6.8’s list with what only deployment reveals — six problems, each stated with what the pilot contributed toward its solution, because a case study that only finds problems has done half its job.

(1) Handheld challenge-verification ergonomics. Step-3 throughput is gated by fixture alignment time, not measurement time: the measurement takes seconds, but positioning the rig against a racked module, achieving standoff tolerance, and confirming fiducial lock averaged four minutes per unit across the S3 campaign, and the technicians’ own suggestions (a self-aligning frame jig, projected alignment guides) are mechanical engineering nobody has funded. The problem is prosaic and decisive: at two minutes per unit, escalated verification prices into routine transactions; at six, it stays exceptional.

(2) Template portability across instrument generations. The pilot’s re-commitment exercise (lesson 6) worked within one vendor’s pipeline — same optics, same feature extraction, versioned parameters. The unsolved case is heterogeneity: an S3-style verification in 2035 will use cameras and extraction software that do not exist today, and nothing yet guarantees that their templates land in a comparable feature space. Cross-vendor template verification standards do not exist (→ Chapter 14, S3), and the pilot’s contribution is a dataset: the 6,300-unit Tier-2 cohort, imaged under two instrument generations, awaiting exactly this research.

(3) Bifacial rear-side condition records. Rear EL in the field remains awkward — access, reflection management, and the racking’s shadowing all degrade image quality — and the pilot’s rear-side evidence is thinner than its front-side evidence in ways an adversary could learn and exploit (a rear-side defect history is effectively unverifiable at V2 today). The candidate answers (rear-biased challenge protocols, thermographic surrogates, sampling modules pulled to ground stations) all cost more than the front-side equivalents, and the honest current posture is the graded one: rear-side claims carry a lower evidence grade, priced accordingly.

(4) Event emission from subcontractor tools. The work-order integration (lesson 3) covered the O&M prime, while sub-tier crews — the cleaning contractor’s crews above all — still route around it, reporting through the prime’s paperwork at day’s end. The S3 pallet-drop finding was exactly this gap. Options run from contractual flow-down (works, slowly, at renewal cadence) to a lightweight signing app for sub-tier use (grade I-C, but an attributed I-C beats an invisible gap) to the structural answer of making event emission a prerequisite for site access badges — which the owner is piloting and the book reports without yet endorsing.

(5) Retrofit enrollment backlog economics. The owner’s other plants want in, and Section 4.3’s retroactive-class discount needs market data it does not yet have (→ Chapter 13): until resale or refinancing events price retroactive-class assets against factory-class ones, the business case for campaign-mode retrofit (as opposed to opportunistic touchpoint enrollment) rests on modeled rather than observed premia. The pilot’s contribution is the cost side: its retrofit trial on a neighboring 12 MW plant measured enrollment at USD 3.10 per module in campaign mode — the denominator waiting for its numerator.

(6) Monitor governance. The cohort monitor, deliberately deprived of write authority (Section 5.5), accumulated something subtler: agenda authority. Its flags determined what the committees discussed, its baselines defined “normal,” and by year-end its maintainers were, in practice, among the most influential parties in the consortium — with no accreditation, no audit schedule, and no adverse-interest rules covering them. Nothing went wrong; the gap is the point. Read-side analytics need governance proportional to their agenda power — versioned models, challengeable baselines, a documented flag taxonomy — and neither this book’s Part III nor the standards landscape yet provides the template.

A closing observation ties the six together: none is a ledger problem. Every open problem the deployment surfaced lives at the physical, procedural, or institutional edges — instruments, templates, sub-tier workflows, market data, analytics governance — which is simultaneously the strongest validation of Part II’s architecture (its own layer held) and the clearest instruction about where this field’s next five years of engineering effort belong.

## 11.8 Illustrative Results

The scattered numbers above, collected for the reader who will be asked “but what did it actually do?” in a steering committee — and, per the book’s evidence discipline, presented with their baselines’ provenance and their caveats attached rather than rounded into a brochure.

Table 11.2 Illustrative year-one results for the composite walkthrough. Evidentiary class per row: I = illustrative estimate from Chapters 6–7 models; A = archetype actual (anonymized program datum, citation pending); B = sector baseline. Baselines for A-rows are insurer and OEM prior-practice figures for comparable assets.

| Metric | Result | Baseline / target | Class |
| --- | --- | --- | --- |
| Tier-0 enrollment marginal cost | < USD 0.08/module (compute + ledger share) | Target ≤ 0.10 | I |
| Added line takt time | 0 s (parallel path) | Target 0 | A |
| Registration lag (median, to anchored DID) | 6.2 h | Anchor-cadence bound | I |
| Enrollment exception rate (steady state) | 0.8% rework loop; 0.02% label mismatch | OEM QA norms | A |
| Commissioning events, Class C conformance | 100% (post-amendment) | — | A |
| Co-signing lag (median / p95, post-amendment) | 9 h / 61 h | Window 72 h | A |
| Insurer diligence cost vs. conventional | ~40% | Prior-year baseline (B) | A |
| S3 verification: template match rate | 378/380 (both mismatches explained) | FA/FR envelope | A |
| S4 adjudication duration | 11 days | Sector norm: months (B) | I |
| Custody retrievability challenge pass rate | 99.4% (one 9-day incident) | SLA 99.9% — breached once | A |
| Consortium infrastructure opex, year one | Within Table 7.4’s plant-scale envelope | Model ±30% | I |
| Governance load | ~340 person-hours consortium-wide | No baseline exists | A |

Three caveats accompany the table in every presentation derived from this walkthrough, and belong here too. Baselines for A-rows are self-reported by interested parties, not independently audited in the manuscript draft. Year-one results measure a fleet too young for degradation disputes, so warranty-relevant numbers (S4) come from a rehearsal scenario, not a live claim. A single walkthrough proves architectural feasibility, not population statistics — the honest claim is that nothing in the architecture’s cost or operability assumptions was falsified by the archetype data available, and several illustrative estimates (enrollment cost, diligence savings, adjudication speed) landed at or better than modeled when checked against those data.

### 11.8.1 What the Program Would Do Differently

The retrospective’s consensus items, in the program’s own priority order. Resource Phase 0 as the main event: the two deferred governance questions became the year’s two incidents, and everyone now believes the causality. Buy the owner’s engineer capacity twice over: the S2 episode was, at root, a staffing decision made against a spreadsheet; evidence requirements change critical-path staffing, and project plans should model co-signing as a resource, not a formality. Integrate the sub-tier from day one: the prime-contractor boundary was known, the gap was documented, and the pallet-drop finding happened anyway — known gaps do not close themselves. Instrument the humans from the start (lesson 7’s metrics were retrofitted at month four; the program would pay real money for the missing four months of baseline). Start the second-site conversation earlier: several design decisions optimal for one plant (single-OEM templates, one work-order integration) acquired inertia that the second site — different OEM, different O&M platform — now has to budget against. None of these is architectural; all of them are expensive; and their absence from the blockchain-for-energy literature the program consulted at kickoff is part of why this chapter exists.

The program’s replication kit — what a successor can take rather than rebuild — is, in the order a successor will want it: the consortium agreement’s structure (Section 10.5’s checklist, now with one jurisdiction’s worked instantiation), the schema and conformance suite (the versioned artifact, portable by design), the contract suite’s two implementations and audit reports, the enrollment-station integration patterns per MES vendor, the reason-code taxonomy, the sampling-design templates, and the metrics definitions of Table 11.2 — so that the second deployment’s results are comparable to the first’s, which is how a pilot becomes an evidence base. [Distribution terms for these artifacts are being settled with the program’s sponsors — TO BE CONFIRMED AT PRESS TIME.]

## 11.9 Chapter Summary

A composite 50 MW design walkthrough instantiated the full stack — Tier-0 enrollment folded invisibly into factory QA with sampled Tier-2 structural defect mapping, active-bound inverters, an eight-validator BFT consortium with twice-redundant public anchoring, three-zone privacy topology, and a four-contract suite small enough to audit twice and change never. The build’s true proportions contradict the industry’s assumptions: constitution and factory integration consumed the calendar; the ledger took six weeks. The five walked scenarios delivered the design’s promises in measurable form: production- paced registration at batch cost with exception statistics the factory came to want for its own reasons; Class-C commissioning that survived its first governance collision and left behind a co-signing-lag metric that now serves as an early-warning instrument; insurer verification at 40% of conventional diligence cost with pre-committed sampling that survived hostile audit review, and two template mismatches that demonstrated the system distinguishing sloppiness from fraud by evidence; an 11-day warranty adjudication whose ledger extracts went uncontested and whose counsel debrief compressed the book’s thesis into a sentence; and an unplanned divestment rehearsal that ran a six-week diligence norm in five days. Table 11.2 collects the numbers with their caveats attached. The failures were procedural and human — unlogged swaps, co-signing bottlenecks, a sleeping custody operator — and the durable lessons are about seams, not algorithms: design the escalations, embed the event emission, staff the instrument operations, measure the humans kindly, and resource the constitution like the main event it is. The pilot also stress-tested Chapter 9’s migration machinery a decade early and found it routine, which is the highest compliment migration machinery can earn — and surfaced, in the monitor’s quiet accumulation of agenda power, a governance gap the literature has not yet named. What remains is to generalize beyond one technology and one plant — Chapter 12 — and to put numbers on the value the pilot only gestured at — Chapter 13.

## References and Further Reading

- International Electrotechnical Commission. IEC 62446-1 (commissioning test documentation) and IEC TS 60904-13 (electroluminescence of photovoltaic modules). Geneva: IEC. The standards whose artifacts the S2 payloads and S3 campaign procedures instantiate.

- IEA-PVPS Task 13. Qualification of Photovoltaic Power Plants Using Mobile Test Equipment. Report T13-24:2021. Field-measurement practice underlying the S3 campaign design.

- International Energy Agency PVPS Task 13. Guidelines for Operation and Maintenance of Photovoltaic Power Plants in Different Climates. Report T13-25:2022.

- Cochran, W. G. Sampling Techniques. 3rd ed. Wiley, 1977 (the S3 sampling design’s textbook basis).

- International Chamber of Commerce. ICC Arbitration Rules. Paris: ICC, 2021.

- [PROGRAM TECHNICAL REPORTS — TITLE, REPORT NUMBER, YEAR — TO BE SUPPLIED WHEN SPONSOR PUBLICATION CLEARANCES ARE COMPLETE. These reports will substantiate Table 11.2 rows marked archetype actual (class A).]